## Parks
Town of Belmont: Priority for ADA Transition Plan - Parks
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Belmont
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Grove Street Park | A. Exterior Access Route | A. Not provided from all site arrival points | Grosvenor Street Parking by Sargent Road and West Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided from all points of arrival including the accessible parking space on Grosvenor Street. (Cost estimate for 40' long by 4' wide asphalt path to the entrance.) | 1 | 1600
2 | Grove Street Park | A. Exterior Access Route | J. Level changes > 1/4" | Route to Batting Cages | Ext. |  | Priority 1 | Program Access | Alter change in level to be 1/4" high max. | 1 | 160
3 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack by Playground | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike racks. (Cost estimate for 30' long by 4' wide asphalt route.) | 1 | 1200
4 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack by Soccer Fields | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike rack. (Cost estimate for 25' long by 4' wide asphalt route.) | 1 | 1000
5 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack by Tennis Courts | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike racks. (Cost estimate for 30' long by 4' wide asphalt route.) | 1 | 1200
6 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack by West Baseball Field | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike rack. (Cost estimate for 20' long by 4' asphalt route.) | 1 | 800
7 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Defibrillator | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the defibrillator. (Cost estimate for 7' long 4' wide asphalt area.) | 1 | 280
8 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Entrance From Grove Street by Basketball Court | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. (Cost estimate for 100' long by 4' wide asphalt route to the basketball court and walking path to the batting cages from the entrance.) | 1 | 4000
9 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Entrance From Grove Street by Basketball Court, Bike Rack | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike racks. (Cost estimate for 30' long by 4' wide asphalt route.) | 1 | 1200
10 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Playground | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to one bench in the playground. (Cost estimate for 10' long by 4' wide asphalt route.) | 1 | 400
11 | Grove Street Park | A. Exterior Access Route | N. Accessible route not provided | Walking Path Behind Northeast Baseball Diamond | Ext. |  | Priority 1 | Program Access | Relocate trash bin to an accessible route. | 1 | 256
12 | Grove Street Park | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces | Parking Lot by Tennis Court | Ext. |  | Priority 1 | Program Access | Provide one van accessible parking space. | 1 | 1850
13 | Grove Street Park | C. Off-Street Parking Lot or Garage | R. Surface not stable, firm, and slip-resistant | Accessible Parking Space on Foster Road | Ext. |  | Priority 1 | Program Access | Repair surface at accessible parking space. | 1 | 192
14 | Grove Street Park | H. Signage | F. Visual characters < 40" above ground | Playground Entrance | Ext. |  | Priority 2 | Navigational Issue | Mount visual sign so that the baseline of the lowest character is 40" min. above the ground. | 1 | 0
15 | Grove Street Park | T. Exterior Benches | A. No accessible route to one bench in area | Bench Under Tree by Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route to this bench. (Cost estimate for 20' long by 4' wide asphalt route.) | 1 | 800
16 | Grove Street Park | A. Drinking Fountains | A. Fountain not on accessible route | Drinking Fountain by Gosvenor Street | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the drinking fountain. (Cost estimate for 6' long by 4' wide route.) | 1 | 240
17 | Grove Street Park | A. Drinking Fountains | H. No drinking fountain provided for standing users | Drinking Fountain by Gosvenor Street | Ext. |  | Priority 1 | Program Access | Provide an additional drinking fountain for standing users. | 1 | 4028
18 | Grove Street Park | B. Play Areas | B. Accessible route not provided around playground | Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route around the play area on the north and northwest side. (Note: Other routes may be too close to the area that is required to be impact attenuating.) (Cost estimate for 103' long by 4' wide asphalt route.) | 1 | 4120
19 | Grove Street Park | B. Play Areas | C. Accessible route not provided to play components | Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 2,948 sq. ft. of poured in place rubber surface.) | 1 | 41272
20 | Grove Street Park | B. Play Areas | K. No compliant transfer system | Playground | Ext. |  | Priority 1 | Program Access | Alteration might be technically infeasible. When replacing surface, attempt to ensure that the transfer platform is 11" to 18" above the ground. | 1 | 0
21 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating C. Field not connected to an accessible route | Northeast Baseball Diamond, First Base Team Seating Area | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Provide an accessible route to the field from the team seating area. (Cost estimate for 6' long by 4' wide asphalt area.) | 1 | 240
22 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating C. Field not connected to an accessible route | Northeast Baseball Diamond, Third Base Team Seating Area | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Provide an accessible route to the field from the team seating area. (Cost estimate for 6' long by 4' wide asphalt area.) | 1 | 240
23 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating C. Field not connected to an accessible route | West Baseball Field, Team Seating by First Base | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Provide an accessible route to the field from the team seating area and from the entrance walkway to the team seating area. (Cost estimate for 50' long by 4' wide asphalt route.) | 1 | 2000
24 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating C. Field not connected to an accessible route | West Baseball Field, Team Seating by Third Base | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Provide an accessible route to the field from team seating. (Cost estimate for 10' by 4' asphalt area.) | 1 | 400
25 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating F. No accessible route to all areas of sport activity | Central Baseball Field by Tennis Courts, First Base Team Seating Area | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Install an accessible route between all areas of sport activity. (Cost estimate for 75' long 4' wide asphalt area.) | 1 | 3000
26 | Grove Street Park | C. Field | A. Accessible spaces not provided at team seating F. No accessible route to all areas of sport activity | Central Baseball Field by Tennis Courts, Third Base Team Seating Area | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at team seating. Install an accessible route between all areas of sport activity including to the team seating area and from the team seating area to the field. (Cost estimate for 40' long by 4' wide asphalt area.) | 1 | 1600
27 | Grove Street Park | C. Field | B. Accessible spaces not provided at sidelines seating F. No accessible route to all areas of sport activity | Central Baseball Field by Tennis Courts | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at sidelines seating on each side. Install an accessible route to each side of bleacher. (Cost estimate for two 10' long by 4' wide asphalt routes.) | 2 | 800
28 | Grove Street Park | C. Field | B. Accessible spaces not provided at sidelines seating F. No accessible route to all areas of sport activity | Northeast Baseball Diamond | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at sidelines seating on each side. Install an accessible route to each side of bleacher. (Cost estimate for two 10' long by 4' wide asphalt routes.) | 2 | 800
29 | Grove Street Park | C. Field | B. Accessible spaces not provided at sidelines seating F. No accessible route to all areas of sport activity | West Baseball Field Spectator Seating | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at sidelines seating. Install an accessible route between the accessible street parking space, the entrance by the bleachers and the bleachers, (Cost estimate for 70' long 4' wide asphalt area.) | 1 | 2800
30 | Grove Street Park | D. Court | C. Court is not connected to an accessible route | Basketball Court | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the court. (Cost estimate for 6' long by 4' wide asphalt route.) | 1 | 240
31 | Grove Street Park | - | - | Tennis Courts | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 10" high solid surface (kickplate) on the push side of all gates. | 1 | 0
32 | Grove Street Park | - |  | Walking Path by Playground Swings | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing clear floor space alongside one bench in each area of the park so that a person using a wheelchair or wheeled mobility device can sit shoulder to shoulder with a person seated on the bench. | 1 | 0
1 | Payson Park | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Elm Street | Ext. |  | Priority 1 | Program Access | Reduce cross slope to be no steeper than 1:50 (2.00%).(Cost estimate to renovate 100' of sidewalk.) | 1 | 4000
2 | Payson Park | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Main Entrance | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost estimate for 10' long, 4' wide asphalt route.) | 1 | 400
3 | Payson Park | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Walkway by Main Entrance | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost estimate for 10' long, 4' wide route.) | 1 | 400
4 | Payson Park | A. Exterior Access Route | J. Level changes > 1/4" | South Payson Street Entrance | Ext. |  | Priority 1 | Program Access | Alter change in level to be 1/4" high max. | 1 | 160
5 | Payson Park | A. Exterior Access Route | N. Accessible route not provided | Band Stand | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. (Cost estimate for 177' long, 4' wide asphalt walkway.) | 1 | 5664
6 | Payson Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack by Main Entrance | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike rack. (Cost estimate for 15' long, 4' wide stone dust route.) | 1 | 480
7 | Payson Park | A. Exterior Access Route | N. Accessible route not provided | Bulletin Board and Defibrillator in Grass Field by Picnic Area | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. (Cost estimate for 24' long, 4' wide asphalt route.) | 1 | 960
8 | Payson Park | A. Exterior Access Route | N. Accessible route not provided | Walking Route Between Playground and South Payson Street Entrance | Ext. |  | Priority 1 | Program Access | Provide an accessible route. (Cost estimate for 4' wide by 109' long asphalt route.) | 1 | 4360
9 | Payson Park | A. Exterior Access Route | N. Accessible route not provided | Walking Route on North Side | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the trash container. (Cost estimate for 6' long by 4' wide asphalt route.) | 1 | 240
10 | Payson Park | G. Entrance | C. Directional sign to accessible entrance not provided | Elm Street Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
11 | Payson Park | G. Entrance | C. Directional sign to accessible entrance not provided | Van Ness Road Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
12 | Payson Park | H. Signage | F. Visual characters < 40" above ground | Main Entrance | Ext. |  | Priority 2 | Navigational Issue | Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. | 1 | 0
13 | Payson Park | S. Picnic Tables | G. Toe or knee clearance at tables not provided | Gravel Picnic Area on Southeast Side | Ext. |  | Priority 1 | Program Access | Provide at least 1 picnic table with knee and toe clearance that is 17" deep minimum. | 1 | 1400
14 | Payson Park | S. Picnic Tables | H. Picnic table not on an accessible route | Gravel Picnic Area on Southeast Side | Ext. |  | Priority 1 | Program Access | Ensure that the dining surface is connected to an accessible route. (Cost estimate for a 75' long, 4' wide asphalt route to the picnic table.) | 1 | 3000
15 | Payson Park | T. Exterior Benches | A. No accessible route to one bench in area | Grass Field by East Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the bench. (Cost estimate for 10' long by 4' wide asphalt route.) | 1 | 400
16 | Payson Park | T. Exterior Benches | A. No accessible route to one bench in area | Walking Route on North Side | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench in this area. (Cost estimate based on 6' long, 4' wide asphalt route.) | 1 | 240
17 | Payson Park | T. Exterior Benches | A. No accessible route to one bench in area | West Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench. (Cost estimate for 4' wide by 5' long asphalt route.) | 1 | 200
18 | Payson Park | B. Play Areas | A. Accessible route not provided to playground | East Playground | Ext. |  | Priority 1 | Program Access | Install an accessible route to the playground. (Cost estimate for 66' long by 4' wide asphalt route.) | 1 | 3300
19 | Payson Park | B. Play Areas | A. Accessible route not provided to playground B. Accessible route not provided around playground | West Playground | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. (Cost estimate for 150 ft. long, 4 ft. wide stone dust route to and around the playground.) | 1 | 4800
20 | Payson Park | B. Play Areas | B. Accessible route not provided around playground | East Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route around the play area (including route to at least one bench). (Cost estimate for 288' long by 4' wide asphalt route around playground.) | 1 | 11520
21 | Payson Park | B. Play Areas | C. Accessible route not provided to play components | East Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 1,250 sq. ft. of poured in place rubber surface.) | 1 | 17500
22 | Payson Park | B. Play Areas | C. Accessible route not provided to play components | West Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 2,917 sq. ft. of poured in place rubber surface.) | 1 | 40838
23 | Payson Park | B. Play Areas | K. No compliant transfer system | West Playground | Ext. |  | Priority 1 | Program Access | Alteration of component might be technically infeasible. When playground is resurfaced with poured-in-place rubber ensure that transfer platform is 11" to 18" high above the ground surface. | 1 | 0
24 | Payson Park | C. Field | C. Field not connected to an accessible route | Grass Field With Soccer Net | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the field. (Cost estimate for 4' wide by 5' long stone dust route.) | 1 | 160
25 | Payson Park |  |  | Grass Field by East Playground | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing clear floor space alongside at least one bench in each area where benches are provided so that a wheelchair user can sit shoulder to shoulder with a person seated at the bench. | 1 | 0
26 | Payson Park |  |  | Gravel Picnic Area on Southeast Side | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide stable, firm and slip resistant walking surface around accessible picnic tables. | 1 | 0
27 | Payson Park |  |  | Van Ness Road Entrance | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing handrails on both sides of stairs. Recommend providing contrasting strips on each stair tread. | 1 | 0
1 | Underwood Park | A. Exterior Access Route | M. Route not maintained in operable working condition | Walkway by South Playground | Ext. |  | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition. | 1 | 160
2 | Underwood Park | A. Exterior Access Route | M. Route not maintained in operable working condition | Sidewalk by Cottage Street Entrance | Ext. |  | Priority 1 | Program Access | Ensure the sidewalk is maintained in operable working condition. | 1 | 0
3 | Underwood Park | A. Exterior Access Route | N. Accessible route not provided | South Playground Trash Bin | Ext. |  | Priority 1 | Program Access | Locate trash bin on an accessible route. | 1 | 0
4 | Underwood Park | A. Exterior Access Route | N. Accessible route not provided | Bike Rack Along Walkway to Cottage Street Entrance | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the bike rack. (Cost estimate for a 6' long 4' wide asphalt route.) | 1 | 240
5 | Underwood Park | H. Signage | F. Visual characters < 40" above ground | Park Entrance Signage | Ext. |  | Priority 2 | Navigational Issue | Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. | 1 | 0
6 | Underwood Park | S. Picnic Tables | G. Toe or knee clearance at tables not provided H. Picnic table not on an accessible route | Main Playground Picnic Table | Ext. |  | Priority 1 | Program Access | Provide at least 1 dining surface that has toe and knee clearance. Locate the dining surface on an accessible route. | 1 | 1400
7 | Underwood Park | T. Exterior Benches | A. No accessible route to one bench in area | Bench by Entrance and Bike Rack | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in the park. (Cost estimate for a 15' long 4' wide asphalt route to the bench.) | 1 | 600
8 | Underwood Park | B. Play Areas | B. Accessible route not provided around playground | South Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route around the play area with the slides and the play area with the swings. (Cost estimate for 256' long 4' wide asphalt route.) | 1 | 10240
9 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | Main Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 1300 sq. ft. of poured in place rubber surface.) | 1 | 18200
10 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | Bucket Swings | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 456 sq. ft. of poured in place rubber surface.) | 1 | 6384
11 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | Standard Swings | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 174 sq. ft. of poured in place rubber surface.) | 1 | 2436
12 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | South Playground, Slide for Young Children | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 376 sq. ft. of poured in place rubber surface.) | 1 | 5264
13 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | South Playground, Slide for Older Children | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 396 sq. ft. of poured in place rubber surface.) | 1 | 5544
14 | Underwood Park | B. Play Areas | C. Accessible route not provided to play components | South Playground, Balance Beam | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 168 sq. ft. of poured in place rubber surface.) | 1 | 2354
15 | Underwood Park | D. Court | C. Court is not connected to an accessible route | Tetherball Court | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the court. (Cost estimate for 84 ft long 4' wide stone dust route.) | 1 | 2688
16 | Underwood Park |  |  | Main Playground Picnic Table | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide min. stable, firm and slip resistant surface under and around an accessible picnic table once it is placed in the picnic area and connected to an accessible route. | 1 | 0
17 | Underwood Park |  |  | Bench by Entrance and Bike Rack | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" wide by 48" deep firm stable and slip resistant clear floor space alongside the bench so that a wheelchair user can sit shoulder to shoulder with a person seated on the bench. | 1 | 0
18 | Underwood Park |  |  | Cottage Street by Park Entrance | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing an on-street accessible parking space and curb ramp by the entrance to the park. | 1 | 0
1 | Winn Brook Park | A. Exterior Access Route | J. Level changes > 1/4" | Tot Lot | Ext. |  | Priority 1 | Program Access | Alter change in level at the base of the ramp to be 1/4" high max. | 1 | 256
2 | Winn Brook Park | A. Exterior Access Route | M. Route not maintained in operable working condition | Playground Walkway | Ext. |  | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition and kept clear of sand. | 1 | 0
3 | Winn Brook Park | A. Exterior Access Route | M. Route not maintained in operable working condition | Playground Walkway | Ext. |  | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition and kept clear. | 1 | 0
4 | Winn Brook Park | A. Exterior Access Route | N. Accessible route not provided | Playground Entrance | Ext. |  | Priority 1 | Program Access | Provide an accessible route. (Cost estimate for a 6' long sloped concrete path with a level landing.) | 1 | 384
5 | Winn Brook Park | A. Exterior Access Route | N. Accessible route not provided | Baseball Diamond Trash Bin | Ext. |  | Priority 1 | Program Access | Relocate the trash bin on the new accessible route. | 1 | 0
6 | Winn Brook Park | A. Exterior Access Route | N. Accessible route not provided | Cross Street Sidewalk | Ext. |  | Priority 1 | Program Access | Provide an accessible route to each bike rack. (Cost estimate based on 46 square ft. of stone dust.) | 1 | 368
7 | Winn Brook Park | A. Exterior Access Route | N. Accessible route not provided | Playground Walkway Trash Bin | Ext. |  | Priority 1 | Program Access | Relocate the trash bin to the edge of the path. | 1 | 0
8 | Winn Brook Park | A. Exterior Access Route | N. Accessible route not provided | Playground Walkway Facing Basketball Court | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the trash bin. (Cost estimate for a 6' long 4' wide concrete route.) | 1 | 384
9 | Winn Brook Park | B. Curb Ramp | A. Curb ramp not provided | Parking Lot to Basketball Court | Ext. |  | Priority 1 | Program Access | Provide a curb ramp at intersection. (Cost estimate for a concrete curb ramp.) | 1 | 2800
10 | Winn Brook Park | B. Curb Ramp | A. Curb ramp not provided | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a curb ramp at intersection. (Cost estimate for a concrete curb ramp.) | 1 | 2800
11 | Winn Brook Park | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide one car accessible parking space and one van accessible parking space. | 2 | 1600
12 | Winn Brook Park | G. Entrance | B. Entrance not on an accessible route C. Directional sign to accessible entrance not provided | Stepped Playground Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance at the exterior of the gate. . | 1 | 346
13 | Winn Brook Park | G. Entrance | K. Maneuvering clearance at door > 1:50 (2.00%) | Cross Street Park Entrance | Ext. |  | Priority 3 | Additional Access | Alter so that the slope in all directions is no greater than 1:50 (2.00%) at the gate. | 1 | 360
14 | Winn Brook Park | H. Signage | Z. Signage not located on an accessible route | Playground Entrance | Ext. |  | Priority 2 | Navigational Issue | Provide an accessible route to the sign. (Cost estimate for a 6' long, 4' wide concrete route.) | 1 | 384
15 | Winn Brook Park | N. Assembly Area | C. Minimum # wheelchair spaces not provided D. Wheelchair spaces not on accessible route | Stage | Ext. |  | Priority 1 | Program Access | Provide one wheelchair accessible space with an accessible route to it. (Recommended location would be in the center of the back row.) | 1 | 300
16 | Winn Brook Park | S. Picnic Tables | G. Toe or knee clearance at tables not provided H. Picnic table not on an accessible route | Playground Walkway on the Northeast Side | Ext. |  | Priority 1 | Program Access | Provide at least 1 picnic table in this area has toe and knee clearance. Ensure that the picnic table is located on an accessible route. | 1 | 1400
17 | Winn Brook Park | S. Picnic Tables | H. Picnic table not on an accessible route | Playground Walkway - Picnic Tables | Ext. |  | Priority 1 | Program Access | Ensure that the accessible picnic table is connected to an accessible route. (Cost estimate for a 6' long, 4' wide concrete route.) | 1 | 384
18 | Winn Brook Park | S. Picnic Tables | H. Picnic table not on an accessible route | Tot Lot Picnic Area | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the accessible picnic table. (Cost estimate for a 10' long, 4' wide stone dust route.) | 1 | 320
19 | Winn Brook Park | T. Exterior Benches | A. No accessible route to one bench in area | Cross Street Sidewalk | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the bench. (Cost estimate for 4' wide, 5' long stone dust route.) | 1 | 160
20 | Winn Brook Park | T. Exterior Benches | A. No accessible route to one bench in area | Playground Walkway on the Northwest Side | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench in this area. (Cost estimate for a 4' wide, 4' long asphalt route.) | 1 | 160
21 | Winn Brook Park | T. Exterior Benches | A. No accessible route to one bench in area | Playground Walkway South Side - Bench Facing Field | Ext. |  | Priority 1 | Program Access | Provide an accessible route to one bench in this area. (Cost estimate for a 4' wide, 4' long stone dust route.) | 1 | 128
22 | Winn Brook Park | T. Exterior Benches | A. No accessible route to one bench in area | Playground Walkway, Bench Facing Basketball Court | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the bench in this area. (Cost estimate for a 4' wide, 4' long stone dust route.) | 1 | 128
23 | Winn Brook Park | B. Play Areas | C. Accessible route not provided to play components | Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. (Cost estimate for 4,070 sq. ft. of poured in place rubber surface.) | 1 | 56980
24 | Winn Brook Park | B. Play Areas | C. Accessible route not provided to play components | Tot Lot | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. Ensure that one bench in this playground is located on an accessible route. (Cost estimate for 1,284 sq. ft. of poured in place rubber surface.) | 1 | 17976
25 | Winn Brook Park | B. Play Areas | N. Play areas not maintained in operable working condition | Tot Lot Ramp | Ext. |  | Priority 1 | Program Access | Ensure play area is maintained in operable working condition. | 1 | 0
26 | Winn Brook Park | C. Field | A. Accessible spaces not provided at team seating | Baseball Diamond | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at both team seating areas and a route to each team seating bench from the new accessible route around the park. (Cost estimate for 4' wide, 16' long stone dust routes.) | 1 | 512
27 | Winn Brook Park | C. Field | F. No accessible route to all areas of sport activity | Soccer and Baseball Fields | Ext. |  | Priority 1 | Program Access | Install an accessible route connecting all areas of sport activity, including routes between the soccer fields, baseball field, tennis courts and basketball court. (Cost estimate for 4' wide 1,515' long stone dust route.) | 1 | 48480
28 | Winn Brook Park |  |  | Tennis Courts | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing benches at tennis courts. | 1 | 0
29 | Winn Brook Park |  |  | Stage | Ext. |  | Priority 4 | Enhanced Usability | As the rise to the stage is less than 6", handrails are not required, but for greater access consider providing circular handrails located between 34"- 38" high and between 18"- 20" high with 12" extensions at the top and bottom of the ramp run. | 1 | 0
30 | Winn Brook Park |  |  | Playground Walkway Bench | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing clear floor space of 36" wide minimum by 48" deep alongside one bench so that a wheelchair user can sit alongside someone sitting on the bench. | 1 | 0
31 | Winn Brook Park |  |  | Playground Walkway - Picnic Tables | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide min. stable, firm and slip resistant surface under and around accessible picnic tables. | 1 | 0
32 | Winn Brook Park |  |  | Tot Lot Ramp | Ext. |  | Priority 4 | Enhanced Usability | IHCD strongly recommends exploring the possibility of an alternative surface to engineered wood fiber (EWF). When used in combination with other surfaces required for accessible routes to play components in Massachusetts, it will present a challenge to prevent level changes at the transition points between EWF and other surfaces, and to keep the accessible routes clear of EWF. | 1 | 0

## Municipal Buildings
Town of Belmont: Priority for ADA Transition Plan - Municipal Buildings
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Belmont
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Beech Street Center | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Egress From East Side of Building to Parking Lot | Ext. |  | Priority 1 | Program Access | Reduce cross slope to be no steeper than 1:50 (2.00%). (Cost for adding concrete to correct pathway cross slope - 10 per square foot.) | 1 | 240
2 | Beech Street Center | A. Exterior Access Route | J. Level changes > 1/4" | Parking Lot | Ext. |  | Priority 1 | Program Access | Alter change in level to be 1/4" high max. (Cost based on a 4'x4' concrete patch.) | 1 | 256
3 | Beech Street Center | A. Exterior Access Route | J. Level changes > 1/4" | Multipurpose Room - Egress Near Kitchen | Ext. |  | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. (Cost based on a 4'x4' concrete patch.) | 1 | 256
4 | Beech Street Center | A. Exterior Access Route | J. Level changes > 1/4" | Egress From Stair 2 | Ext. |  | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. (Cost based on a 4'x4' concrete patch.) | 1 | 256
5 | Beech Street Center | A. Exterior Access Route | N. Accessible route not provided | Lending Library Book Exchange on Beech Street at Building Entrance | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. Provide a 4' wide min. 6' long asphalt path to book exchange. Ensure path has a maximum running slope of 1:20 (5.00%) and a maximum cross slope of 1:50 (2.00%). (Cost for a new concrete route.) | 1 | 384
6 | Beech Street Center | C. Off-Street Parking Lot or Garage | A. Total # of parking C. Total # of designated van accessible spaces B. Total # of designated accessible parking spaces P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 2 | 0
7 | Beech Street Center | C. Off-Street Parking Lot or Garage | P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 1 | 0
8 | Beech Street Center | C. Off-Street Parking Lot or Garage | P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 4 | 0
9 | Beech Street Center | A. Means of Egress | B. Tactile exit sign not provided | Multipurpose Room | 1 | 119 | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
10 | Beech Street Center | A. Means of Egress | B. Tactile exit sign not provided | Stair 2 | 2 | 207 | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
11 | Beech Street Center | A. Means of Egress | B. Tactile exit sign not provided O. Illuminated ISA symbol not provided (MAAB) | Main Entrance | Ext. |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
12 | Beech Street Center | A. Means of Egress | B. Tactile exit sign not provided O. Illuminated ISA symbol not provided (MAAB) | Multipurpose Room | 1 | 119 | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility at the accessible exit with the illuminated exit sign. | 1 | 432
13 | Beech Street Center | A. Means of Egress | B. Tactile exit sign not provided O. Illuminated ISA symbol not provided (MAAB) | Egress Near Game Room | 1 | 122 | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
14 | Beech Street Center | B. Interior Access Route | A. Route < 36" wide | Counseling Room | 1 |  | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
15 | Beech Street Center | B. Interior Access Route | B. Obstructed by protruding objects | Stair 1 | 1 | 130 | Priority 3 | Additional Access | Provide a cane-detectable barrier at the water control. Also relocate stored items out of stairway landing. | 1 | 306
16 | Beech Street Center | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women’s Toilet Room | 1 |  | Priority 3 | Additional Access | Remove the trash container to provide maneuvering clearance at the door. | 1 | 0
17 | Beech Street Center | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Library - Egress to Patio on East Side of Building | 1 | 121 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
18 | Beech Street Center | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Single-User Toilet Room | 2 | 211 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
19 | Beech Street Center | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Stair 2 | 2 | 207 | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
20 | Beech Street Center | H. Signage | C. Raised characters < 48" or > 60" above ground | Stair 2 | 2 | 207 | Priority 2 | Navigational Issue | Mount signs so that the baseline of the lowest tactile character is 48” min. above finished floor and the baseline of the highest tactile character is 60” max. above the finished floor. | 1 | 0
21 | Beech Street Center | H. Signage | G. Sign not located on the latch side of the door | Multipurpose Room | 1 | 119 | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
22 | Beech Street Center | K. Operable Parts | B. Clear floor space is not provided | Classroom B | 2 | 206 | Priority 3 | Additional Access | Clear floor space not provided at sign. Relocate sign closer to latch/mount on glass. | 1 | 0
23 | Beech Street Center | K. Operable Parts | D. Side reach > 54" | Multipurpose Room | 1 | 119 | Priority 3 | Additional Access | Provide a clothes rod or coat hook no higher than 48" above the finished floor. | 1 | 256
24 | Beech Street Center | K. Operable Parts | D. Side reach > 54" | Arts and Crafts Room | 1 | 125 | Priority 3 | Additional Access | Provide a clothes rod or coat hook no higher than 48" above the finished floor. | 1 | 256
25 | Beech Street Center | K. Operable Parts | H. Not operable with a closed fist | Single-User Toilet Room | 2 | 211 | Priority 3 | Additional Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 563
26 | Beech Street Center | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Patio on East Side of Building | Ext. |  | Priority 1 | Program Access | Provide at least 1 dining surface in this area with 30" wide min. and 17" deep min. toe clearance. (This table does have the 27" min. required knee clearance.) | 1 | 1100
27 | Beech Street Center | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Lounge Area | 1 | 121 | Priority 1 | Program Access | Provide at least 1 dining surface in this area with 30" wide min. and 17" deep min. toe clearance. (This table does have the 27" min. required knee clearance.) | 1 | 1100
28 | Beech Street Center | N. Assembly Area | P. Assistive listening devices not provided | Multipurpose Room | 1 | 119 | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1214
29 | Beech Street Center | T. Exterior Benches | A. No accessible route to one bench in area N. Accessible route not provided | Patio on East Side of Building | Ext. |  | Priority 1 | Program Access | Relocate at least one bench in this area to an accessible route and provide an accessible route from the patio connecting to the bocce ball court and to at least one bench of the north side of the bocce court.) (Cost based on a 4' wide x 30' long concrete path with a max. running slope of 1:20 (5.00%) and a max. cross slope of 1:50 (2.00%) as shown in Figure 1 of the narrative.) | 1 | 1920
30 | Beech Street Center | C. Single-User Toilet | H. Rear grab bar > 42" long (MAAB) | Single-User Toilet Room | 1 | 129 | Priority 3 | Additional Access | Provide a rear wall grab bar that is 42" long min. and extends from the toilet 12" min. on one side and 24" min. on the other side (open side). | 1 | 898
31 | Beech Street Center | E. Urinal | D. Urinal recessed > 24" has > 36" clear width | Men’s Toilet Room | 2 | 205 | Priority 3 | Additional Access | If urinal is recessed greater than 24" ensure there is a clear width of 36". (Cost to relocate the wall at the urinal where the width is narrower than allowed, or to move the urinal out from the back wall to a location that is recessed no more than 24” is beyond scope of this project.) | 1 | 0
32 | Beech Street Center | A. Drinking Fountains | K. Standing height fountain does not have cane protection | Near Multipurpose Room | 1 | Hallway | Priority 3 | Additional Access | Provide a cane-detectable barrier skirt under the high unit. | 1 | 890
33 | Beech Street Center | B. Sink | A. Clear floor space not provided at sink | Lounge Area | 1 | 121 | Priority 3 | Additional Access | Provide a 30" by 48" clear floor space positioned for a forward approach. (Relocate watering can.) | 1 | 0
34 | Beech Street Center | B. Sink | A. Clear floor space not provided at sink | Classroom A | 2 | 215 | Priority 3 | Additional Access | Provide a 30" by 48" clear floor space positioned for a forward approach. (Relocate broom and any other stored items from clear floor space under sink.) | 1 | 0
35 | Beech Street Center | B. Sink | B. Toe and knee clearances not provided | Health Room | 2 | 210 | Priority 1 | Program Access | Ensure there is a 27" knee clearance positioned for a forward approach. | 1 | 1686
36 | Beech Street Center | F. Exercise Machines | A. Clear floor space not provided | Fitness | 2 | 209 | Priority 3 | Additional Access | Ensure that one of each type of equipment has a 30" by 48" clear floor space positioned for transfer or for use by an individual seated in a wheelchair. Clear floor space required at exercise machines and equipment shall be permited to overlap. | 1 | 0
37 | Beech Street Center | Patio |  | Patio on Southeast Side of Building | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a sign indicating the direction of the accessible route when exiting the multipurpose room. | 1 | 0
1 | Fire Station 2 | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces P. Sign bottom < 60" above finished grade | Parking | Ext. |  | Priority 1 | Program Access | Locate the van accessible sign with the bottom of the sign 60" min. above the ground. | 1 | 0
2 | Fire Station 2 | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Main Entrance (Egress) | 1 |  | Priority 1 | Program Access | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
3 | Fire Station 2 | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
4 | Fire Station 2 | H. Signage | B. Raised characters not provided on sign | Study | 2 | 201 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on sign. Some raised characters are missing from the sign. | 1 | 232
5 | Fire Station 2 | H. Signage | G. Sign not located on the latch side of the door | Toilet Rooms - Main Entrance | 1 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 2 | 0
6 | Fire Station 2 | K. Operable Parts | C. Reach < 15" or > 48"(forward/side approach) | Main Entrance | 1 |  | Priority 3 | Additional Access | Relocate telephone to be no higher than 48" above the finished floor. | 1 | 0
7 | Fire Station 2 | C. Single-User Toilet | M. Dispenser mounted over grab bar | Men's and Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate paper towel dispenser so that it is not mounted above the grab bar. | 2 | 512
8 | Fire Station 2 |  |  | Stair 1 | 1 |  | Priority 4 | Enhanced Usability | Recommend providing contrast strips at each stair tread. | 1 | 0
9 | Fire Station 2 |  |  | Stair Exit Sign From Stair 2 | 1 |  |  |  | Good example of a raised character and braille egress sign. | 1 | 0
10 | Fire Station 2 |  |  | Corridor | 2 |  |  |  | This is a good example of recessing a fire extinguisher cabinet. | 1 | 0
11 | Fire Station 2 |  |  | Main Entrance | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing contrast strips at each stair tread. | 1 | 0
1 | Fire Station Headquarters | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Main Entrance | 1 |  | Priority 1 | Program Access | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
2 | Fire Station Headquarters | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women’s Toilet Room | 2 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
3 | Fire Station Headquarters | H. Signage | B. Raised characters not provided on sign |  | 1 |  | Priority 2 | Navigational Issue | Raised character "R" missing on sign. Provide text with all characters raised. (Replace or repair sign.) | 1 | 232
4 | Fire Station Headquarters | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign | Assistant Chief’s Office | 2 | 208 | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on sign. (Replace sign.) | 1 | 232
5 | Fire Station Headquarters | J. Service Counter | B. Counter > 36" high | Administration Chief’s Office | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880
6 | Fire Station Headquarters | J. Service Counter | B. Counter > 36" high | Fire Prevention | 2 | 210 | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880
7 | Fire Station Headquarters | N. Assembly Area | P. Assistive listening devices not provided | Training Room | 2 | 201 | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1214
8 | Fire Station Headquarters | F. Dispensers | Paper towel dispenser mounted above grab bar. | Single-User Toilet Room in Garage | 1 |  | Priority 3 | Additional Access | Relocate paper towel dispenser so it is not located above the grab bar (MAAB). | 1 | 256
9 | Fire Station Headquarters | F. Dispensers | Paper towel dispenser mounted above grab bar. | Men's Single-User Toilet Room in Lobby | 1 |  | Priority 3 | Additional Access | Relocate paper towel dispenser so it is not located above the grab bar (MAAB). | 1 | 256
10 | Fire Station Headquarters | F. Dispensers | Paper towel dispenser mounted above grab bar. | Men’s Single-User Toilet Room | 2 |  | Priority 3 | Additional Access | Relocate paper towel dispenser so it is not located above the grab bar (MAAB). | 1 | 256
11 | Fire Station Headquarters | F. Dispensers | Paper towel dispenser mounted above grab bar. | Women’s Single-User Toilet Room | 2 |  | Priority 3 | Additional Access | Relocate paper towel dispenser so it is not located above the grab bar (MAAB). | 1 | 256
12 | Fire Station Headquarters | A. Drinking Fountains | H. No drinking fountain provided for standing users | Training Room | 2 | 201 | Priority 1 | Program Access | Provide an additional drinking fountain for standing users or install a Hi-Lo drinking fountain. | 1 | 4028
13 | Fire Station Headquarters | Podium |  | Training Room | 2 | 201 | Priority 4 | Enhanced Usability | Recommend providing and adjustable height podium with 27" min. knee and toe clearance. | 1 | 0
14 | Fire Station Headquarters | Sign |  | Men’s Toilet Room | 2 |  | Priority 4 | Enhanced Usability | Recommend, if it is preferred to have a single-user men's and a single-user women's toilet room on each floor, to get signage that shows the International Symbol of Accessibility (ISA) with raised characters and braille with pictograms that show the intended gender in each case. | 2 | 0
15 | Fire Station Headquarters | Sign |  | Women’s Toilet Room | 2 |  | Priority 4 | Enhanced Usability | Recommend, if it is preferred to have a single-user men's and a single-user women's toilet room on each floor, to get signage that shows the International Symbol of Accessibility (ISA) with raised characters and braille with pictograms that show the intended gender in each case. | 2 | 0
1 | Homer Municipal Building | A. Exterior Access Route | N. Accessible route not provided | Path to Street | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike rack that is firm, stable and slip resistant and with a maximum slope of 2% in all directions at the bike rack. (Cost to provide an asphalt patch with a 2% max. slope or to relocate bike rack to an accessible location.). | 1 | 240
2 | Homer Municipal Building | G. Entrance | C. Directional sign to accessible entrance not provided | Egress/ Entrance At Staircase 2 | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
3 | Homer Municipal Building | G. Entrance | C. Directional sign to accessible entrance not provided | Egress/Non-Accessible Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
4 | Homer Municipal Building | A. Means of Egress | B. Tactile exit sign not provided | Staircase 1 | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
5 | Homer Municipal Building | A. Means of Egress | B. Tactile exit sign not provided | Staircase 2 | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
6 | Homer Municipal Building | B. Interior Access Route | B. Obstructed by protruding objects | Women’s Toilet Room | 3 |  | Priority 3 | Additional Access | Wrap pipes with padding at all points below 80" above the finished floor to prevent head injury. | 1 | 0
7 | Homer Municipal Building | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Facilities Department | G |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
8 | Homer Municipal Building | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men's Toilet Room | 2 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
9 | Homer Municipal Building | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women’s Toilet Room | 3 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
10 | Homer Municipal Building | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men’s Toilet Room | 3 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
11 | Homer Municipal Building | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Gallery Second Entrance | 3 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
12 | Homer Municipal Building | E. Stairways | E. Handrails have non-compliant cross section | Staircase 1 | 1 |  | Priority 3 | Additional Access | Provide handrails on one side of egress stairs (side with noncompliant wood handrails) with 1 1/4" - 2" circular cross sections from the ground floor to floors one, two and three. (Cost based on 90' of compliant wall mounted metal handrails.) | 1 | 6660
13 | Homer Municipal Building | E. Stairways | E. Handrails have non-compliant cross section | Staircase 2 | 3 |  | Priority 3 | Additional Access | Provide handrails on one side of egress stairs (side with noncompliant wood handrails) with 1 1/4" - 2" circular cross sections from the ground floor to floors one, two and three. (Cost based on 90' of compliant wall mounted metal handrails.) | 1 | 6660
14 | Homer Municipal Building | H. Signage | C. Raised characters < 48" or > 60" above ground | DPW | 1 |  | Priority 2 | Navigational Issue | Mount signs so that the baseline of the lowest tactile character is 48” min. above finished floor and the baseline of the highest tactile character is 60” max. above the finished floor. | 1 | 0
15 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Staircase 1 | 2 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. (The existing sign can remain, but add an additional accessible sign on the glass on the latch side of the door. People who are blind or low vision are taught to find the door handle and reach up from there to locate the accessible sign, and such visitors would likely never find the existing sign.) | 1 | 232
16 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Entrance | 2 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. (The existing sign can remain, but add an additional accessible sign on the glass on the latch side of the door. People who are blind or low vision are taught to find the door handle and reach up from there to locate the accessible sign, and such visitors would likely never find the existing sign.) | 1 | 232
17 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Egress | 2 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
18 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Entrance | 3 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. (The existing sign can remain, but add an additional accessible sign on the glass on the latch side of the door. People who are blind or low vision are taught to find the door handle and reach up from there to locate the accessible sign, and such visitors would likely never find the existing sign.) | 1 | 232
19 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Egress | 3 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. (The existing sign can remain, but add an additional accessible sign on the glass on the latch side of the door. People who are blind or low vision are taught to find the door handle and reach up from there to locate the accessible sign, and such visitors would likely never find the existing sign.) | 1 | 232
20 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Gallery | 3 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
21 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Gallery Second Entrance | 3 |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
22 | Homer Municipal Building | H. Signage | G. Sign not located on the latch side of the door | Facilities Department | G |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
23 | Homer Municipal Building | J. Service Counter | B. Counter > 36" high | Facilities Department | G |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880
24 | Homer Municipal Building | J. Service Counter | B. Counter > 36" high | Board of Health and Veterans Services | 2 |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground or finished floor. | 1 | 880
25 | Homer Municipal Building | K. Operable Parts | B. Clear floor space is not provided | Men’s Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate table to provide a 30" min. by 48" min. clear floor space at the sign to the toilet room. | 1 | 0
26 | Homer Municipal Building | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Board of Assessors | 1 |  | Priority 1 | Program Access | Provide at least 1 dining or work surface with 27" min. knee and toe clearance. | 1 | 700
27 | Homer Municipal Building | M. Dining or Work Surfaces | D. Top of work surface < 28" or > 34" | Treasurer | 1 |  | Priority 3 | Additional Access |  | 1 | 0
28 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Men’s Toilet Room | G |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
29 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Women’s Toilet Room | G |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
30 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Men’s Toilet Room | 1 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
31 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Women’s Toilet Room | 1 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
32 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Women’s Toilet Room | 2 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
33 | Homer Municipal Building | C. Single-User Toilet | O. Hook located > 48" high | Men's Toilet Room | 2 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
1 | Main Library | A. Exterior Access Route | C. Exterior route < 48" wide | South of Library - Picnic Area | Ext. |  | Priority 3 | Additional Access | Provide a firm, stable and slip resistant path with a clear width of 48" min. to the picnic tables. Ensure path has a cross slope no steeper than 1:50 (2.00%), and a running slope no steeper than 1:20 (5%). | 1 | 600
2 | Main Library | A. Exterior Access Route | M. Route not maintained in operable working condition | Walkway at East Side of Building | Ext. |  | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition. (Repair deteriorated cement in walkway.) (Cost based on two 4'x4' concrete patches.) | 2 | 512
3 | Main Library | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces J. Access aisle < 60" wide at car/van space K. Access aisle < 96" wide at van space O. Sign does not have the designation "Van Accessible" | West Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a van accessible parking space at least 96" wide with a marked access aisle at least 96" wide. Add the designation "Van Accessible" to the sign at the van accessible space. Provide a marked access aisle that is at least 60" wide at the car accessible parking space. (Re-stripe access aisle to 96" wide min.). Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 800
4 | Main Library | G. Entrance | B. Entrance not on an accessible route C. Directional sign to accessible entrance not provided | West Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
5 | Main Library | G. Entrance | C. Directional sign to accessible entrance not provided | East Entrance | G |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
6 | Main Library | A. Means of Egress | B. Tactile exit sign not provided | Main Entrance From North Side of Building | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
7 | Main Library | A. Means of Egress | B. Tactile exit sign not provided | Assembly Room - Egress to East Parking Lot | G |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
8 | Main Library | A. Means of Egress | B. Tactile exit sign not provided O. Illuminated ISA symbol not provided (MAAB) | West Entrance | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
9 | Main Library | A. Means of Egress | B. Tactile exit sign not provided O. Illuminated ISA symbol not provided (MAAB) | East Entrance | G |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 432
10 | Main Library | B. Interior Access Route | A. Route < 36" wide | Newspapers and Magazines - West Side of Building | 1 |  | Priority 3 | Additional Access | Relocate chairs to ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
11 | Main Library | B. Interior Access Route | A. Route < 36" wide | Young Adult Section - East Side of Building | 1 |  | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
12 | Main Library | B. Interior Access Route | A. Route < 36" wide | Children’s Library | G |  | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
13 | Main Library | Benches |  | South of Library - Picnic Area | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a firm, stable and slip resistant clear floor space alongside at least one bench in each sitting area so that a person using a wheelchair can sit shoulder-to-shoulder with a person seated on the bench. Also recommend providing at least one bench with arms. | 1 | 0
14 | Main Library | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 3 | Additional Access | Minimum require 18" pull-side maneuvering clearance not provided. Provide an automatic door opener. | 1 | 3060
15 | Main Library | C. Doors, Doorways, & Gates | F. Maneuvering clearance at door > 1:50 (2.00%) | East Entrance | Ext. |  | Priority 3 | Additional Access | Alter so that the slope in all directions at the doorway landing is no greater than 1:50 (2.00%). | 1 | 200
16 | Main Library | C. Doors, Doorways, & Gates | L. Hardware not operable with a closed fist | Claflin Room - Northwest Side of Building | 1 |  | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
17 | Main Library | C. Doors, Doorways, & Gates | L. Hardware not operable with a closed fist | Ground Level Central Hallway | G |  | Priority 1 | Program Access | Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
18 | Main Library | G. Elevator | B. Elevator call buttons > 48" | Elevator | B |  | Priority 3 | Additional Access | Lower call buttons to 48" max. above the finished floor. | 1 | 1928
19 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Newspapers and Magazines - West Side of Building | 1 |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
20 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Claflin Room - Northwest Side of Building | 1 |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
21 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Claflin Room - Northwest Side of Building | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on sign. Provide braille on sign. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
22 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Young Adult Section - East Side of Building | 1 |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
23 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Assembly Room | G |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
24 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
25 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Flett Room | G |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
26 | Main Library | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Children’s Library | G |  | Priority 2 | Navigational Issue | At permanent rooms where signage is provided, provide text with raised characters duplicated in braille on sign. Mount visual sign so that the baseline of the lowest character is 40" min. above the finished floor. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
27 | Main Library | K. Operable Parts | D. Side reach > 54" | Assembly Room | G |  | Priority 3 | Additional Access | Relocate or provide at least one coat rod between 15" - 48" above the finished floor. | 1 | 256
28 | Main Library | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Reference Room Computer Terminal - South Side of Building | 1 |  | Priority 1 | Program Access | Provide a comparable terminal on a work surface with 27" min. knee and toe clearance. | 1 | 0
29 | Main Library | M. Dining or Work Surfaces | D. Top of dining/work surface < 28" or > 34" | Stacks B04 Near Stair B06 | B |  | Priority 3 | Additional Access | Provide a comparable computer terminal on an accessible work surface with tops between 28"- 34" above the floor and 27" clear height underneath. | 1 | 0
30 | Main Library | N. Assembly Area | N. Accessible route to stage not provided | Assembly Room | G |  | Priority 1 | Program Access | Provide an accessible route to the stage. Provide a portable ramp. | 1 | 500
31 | Main Library | N. Assembly Area | P. Assistive listening devices not provided | Assembly Room | G |  | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 1214
32 | Main Library | Picnic Tables |  | South of Library - Picnic Area | Ext. |  | Priority 4 | Enhanced Usability | Recommend proving a 48" min. firm, stable and slip resistant surface around the exterior of each accessible picnic table in the library. | 1 | 0
33 | Main Library | S. Picnic Tables | G. Toe or knee clearance at tables not provided | South of Library - Picnic Area | Ext. |  | Priority 1 | Program Access | Provide at least 1 picnic table (or ensure that 5% of picnic tables) have toe and knee clearance. | 1 | 1400
34 | Main Library | A. Overall Access | B. Turning space not provided E. Sign to accessible toilet not provided | Toilet Room in Central Hallway | 1 |  | Priority 1 | Program Access | Provide a directional sign on the exterior door indicating the location of the nearest accessible toilet or bathing room. | 1 | 232
35 | Main Library | A. Overall Access | E. Sign to accessible toilet not provided | Central Hallway of Main Floor | 1 |  | Priority 2 | Navigational Issue | Provide a directional sign indicating the location of the nearest accessible toilet or bathing room. | 1 | 232
36 | Main Library | A. Overall Access | E. Sign to accessible toilet not provided | Ground Level Central Hallway - Toilet Rooms | G |  | Priority 2 | Navigational Issue | Provide a directional sign indicating the location of the nearest accessible toilet or bathing room. | 1 | 232
37 | Main Library | A. Overall Access | E. Sign to accessible toilet not provided | Children’s Library | G |  | Priority 2 | Navigational Issue | Provide a directional sign indicating the location of the nearest accessible toilet or bathing room. | 1 | 232
38 | Main Library | B. Lavatory | E. Plumbing underneath is exposed | Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
39 | Main Library | F. Dispensers | D. Dispenser acts as a protruding object | Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 3 | Additional Access | Relocate paper towel dispenser out of the circulation path or provide a cane-detectible barrier below the dispenser 27" max. above the finished floor. | 1 | 306
40 | Main Library | F. Dispensers | D. Dispenser acts as a protruding object | Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 3 | Additional Access | Changing station not in operable working condition. Repair so table surface can be left in upright position. | 1 | 0
41 | Main Library | A. Drinking Fountains | H. No drinking fountain provided for standing users | Near Accessible Toilet Room - Ground Level Central Hallway | G |  | Priority 1 | Program Access | Provide an additional drinking fountain for standing users or install a Hi-Lo drinking fountain. | 1 | 4028
42 | Main Library | A. Drinking Fountains | H. No drinking fountain provided for standing users | Children’s Library | G |  | Priority 1 | Program Access | Provide an additional drinking fountain for standing users or install a Hi-Lo drinking fountain. | 1 | 4028
43 | Main Library | Circulation Desk |  | Circulation Desk Near North Side of Building | 1 |  |  |  |  | 1 | 0
44 | Main Library | Staircase |  | Stair B03 | B |  | Priority 4 | Enhanced Usability | Recommend providing rail extension on both sides of all stairway railings in the library that extend 12" beyond the top and bottom riser. Also recommend providing color contrasting strips on stairway treads. | 1 | 0
1 | Town Hall | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) L. Does not prevent accumulation of water | Concord Avenue | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). Repair surface. (Cost estimate for 10' long by 4' wide area.) | 1 | 400
2 | Town Hall | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Moore Street Sidewalk | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost estimate for 20' long by 4' wide area.) | 1 | 800
3 | Town Hall | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route to Bench | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost estimate for 30' long asphalt route.) | 1 | 1200
4 | Town Hall | A. Exterior Access Route | N. Accessible route not provided | Bike Rack | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the bike rack. (Cost estimate for a 6' long, 4' wide asphalt route.) | 1 | 240
5 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit | Southwest Exit | 1 |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
6 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit | Route to Exterior Egress Stair | 2R |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
7 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit | Egress From Dressing Room Level | B |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
8 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit | Main Entrance (Egress) | G |  | Priority 1 | Program Access | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
9 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit C. Directional sign to accessible emergency exit not provided | Stair 1 | G |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. | 1 | 464
10 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit C. Directional sign to accessible emergency exit not provided R. Door requires > 15 lbs. of force to open | Southwest Exit | G |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. Adjust closers of exterior doors so doors do not require more than 15 pounds of force. | 1 | 464
11 | Town Hall | H. Emergency Exit | B. Tactile sign not provided at exit R. Door requires > 15 lbs. of force to open | Northwest Exits | 1 |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Adjust closers of exterior doors so doors do not require more than 15 pounds of force. | 2 | 464
12 | Town Hall | H. Emergency Exit | D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Main Entrance (Egress) | G |  | Priority 2 | Navigational Issue | If an illuminated exit sign is provided, provide an illuminated sign with the International Symbol of Accessibility at this exit. | 1 | 0
13 | Town Hall | A. Means of Egress | B. Tactile exit sign not provided | Auditorium Exits | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 3 | 696
14 | Town Hall | A. Means of Egress | B. Tactile exit sign not provided | Auditorium | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
15 | Town Hall | A. Means of Egress | B. Tactile exit sign not provided | Auditorium Exit Leading to Elevator Next to Town Administrator | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
16 | Town Hall | A. Means of Egress | B. Tactile exit sign not provided | Balcony Exits | 2 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 2 | 464
17 | Town Hall | A. Means of Egress | B. Tactile exit sign not provided | Stair Egress by Human Resources | 2F |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
18 | Town Hall | B. Interior Access Route | B. Obstructed by protruding objects | Defibrillator by Elevator | 1 |  | Priority 3 | Additional Access | Relocate defibrillator. | 1 | 0
19 | Town Hall | B. Interior Access Route | H. Accessible route not provided | Stairs to Dressing Rooms | B |  | Priority 1 | Program Access | Provide an accessible route between the stage and dressing rooms. (Cost estimate for a 2-stop Limited Use Limited Access Application [LULA] elevator.) | 1 | 90000
20 | Town Hall | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women's Toilet Room on Southwest | 1 |  | Priority 3 | Additional Access | Relocate trash bin. | 1 | 0
21 | Town Hall | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Platform Lift to Stage | 1 |  | Priority 3 | Additional Access | Relocate stored items so that there is maneuvering clearance at the door to the lift. | 1 | 0
22 | Town Hall | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Women's Toilet Room | G |  | Priority 3 | Additional Access | Relocate trash bin. | 1 | 0
23 | Town Hall | C. Doors, Doorways, & Gates | K. Threshold > 1/2" high | Door by Stage | 1 |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. | 1 | 150
24 | Town Hall | C. Doors, Doorways, & Gates | K. Threshold > 1/2" high | Auditorium Door to Corridor | 1 |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. | 1 | 150
25 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women's Toilet Room on Southwest | 1 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
26 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men's Toilet Room on West | 1 |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
27 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Corridor Door to Toilet Rooms | G |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
28 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Women's Toilet Room | G |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
29 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Men's Toilet Room | G |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
30 | Town Hall | C. Doors, Doorways, & Gates | M. Door requires > 5 lbs. of force to open | Single-User Toilet Room | G |  | Priority 3 | Additional Access | Adjust closers so doors do not require more than 5 pounds of force to open. | 1 | 0
31 | Town Hall | E. Stairways | C. Handrail not provided on both sides | Stair to Floor 2R | 2R |  | Priority 3 | Additional Access | Provide a handrail on each side. | 1 | 1320
32 | Town Hall | E. Stairways | D. Handrails do not extend 12" from stairs | Staircase From Ground Floor to First Floor | G |  | Priority 3 | Additional Access | Bottom: Ensure handrails extend to one tread depth beyond the last riser (on the left handrail). | 1 | 332
33 | Town Hall | E. Stairways | F. Handrails not continuous where required | Stair 1 | 1 |  | Priority 3 | Additional Access | Provide a continuous handrail on the interior side of stair. | 1 | 1320
34 | Town Hall | H. Signage | G. Sign not located on the latch side of the door | Credit Union Office | 2R |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
35 | Town Hall | H. Signage | G. Sign not located on the latch side of the door | Men's Toilet Room | G |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
36 | Town Hall | J. Service Counter | E. Surface not stable, firm, and slip-resistant | Town Administrator's | 1 |  | Priority 3 | Additional Access | Secure the mat. | 1 | 0
37 | Town Hall | K. Operable Parts | C. Reach < 15" or > 48"(forward/side approach) | Select Board Meeting Room | 1 |  | Priority 3 | Additional Access | Provide a clothes rack that is located no higher than 48" above the finished floor. | 1 | 100
38 | Town Hall | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Select Board Meeting Room | 1 |  | Priority 1 | Program Access | Provide at least 1 work surface with 27" min. knee and toe clearance. | 1 | 1100
39 | Town Hall | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Human Resources Director | 2F |  | Priority 1 | Program Access | Provide at least 1 work surface with toe clearance. | 1 | 700
40 | Town Hall | N. Assembly Area | P. Assistive listening devices not provided | Auditorium | 1 |  | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system and signage notifying visitors of the assistive listening system. (Cost estimate for capacity of 250 people.) | 1 | 3941
41 | Town Hall | S. Picnic Tables | H. Picnic table not on an accessible route | Shaded Picnic Area | Ext. |  | Priority 1 | Program Access | Ensure that the dining surface is connected to an accessible route. (Cost estimate for a 10' long by 4' wide asphalt route to the picnic table.) | 1 | 400
42 | Town Hall | S. Picnic Tables | H. Picnic table not on an accessible route | Sunny Picnic Area on Concord Avenue | Ext. |  | Priority 1 | Program Access | Ensure that the dining surface is connected to an accessible route. (Cost estimate for a 15' long by 4' wide asphalt route to the picnic table.) | 1 | 600
43 | Town Hall | T. Exterior Benches | A. No accessible route to one bench in area | Sunny Picnic Area on Concord Avenue | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the bench. (Cost estimate for a 20' long by 4' wide asphalt route.) Alternatively relocate the bench. | 1 | 800
44 | Town Hall | A. Overall Access | G. 6 fixtures, but no ambulatory compartment provided | Women's Toilet Room | G |  | Priority 1 | Program Access | Provide one ambulatory accessible compartment. | 1 | 3012
45 | Town Hall | C. Single-User Toilet | O. Hook located > 48" high | Single-User Toilet Room | 2F |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
46 | Town Hall | D. Toilet Compartment | D. Door has malfunctioning self-closing hinge | Women's Toilet Room | G |  | Priority 3 | Additional Access | Repair hinge. | 1 | 0
47 | Town Hall | D. Toilet Compartment | R. Coat hook > 48" | Men's Toilet Room | G |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
48 | Town Hall | F. Dispensers | A. Controls > 42" high C. Not operable with a closed fist | Single-User Toilet Room | 2F |  | Priority 3 | Additional Access | Relocate so the operable part is 42" max. above the finished floor. Provide a dispenser that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 1353
49 | Town Hall | F. Dispensers | D. Dispenser acts as a protruding object | Women's Toilet Room on Southwest | 1 |  | Priority 3 | Additional Access | Relocate paper towel dispenser out of the circulation path. | 1 | 256
50 | Town Hall | J. Changing Rooms | D. Bench not provided N. Hook > 48" high | Dressing Room 3 | B |  | Priority 1 | Program Access | Provide a 48" long 24" wide accessible bench with clear floor space alongside it within the room. Locate hook no higher than 48" above the finished floor. | 1 | 350
51 | Town Hall | A. Drinking Fountains | G. Inadequate water flow H. No drinking fountain provided for standing users | Corridor by Town Clerk | G |  | Priority 1 | Program Access | Repair drinking fountain to provide adequate water flow. Provide an additional drinking fountain for standing users. | 1 | 4028
52 | Town Hall | A. Drinking Fountains | H. No drinking fountain provided for standing users | Corridor by West Side Toilet Rooms | 1 |  | Priority 1 | Program Access | Provide an additional drinking fountain for standing users. | 1 | 4028
53 | Town Hall | A. Drinking Fountains | K. Standing height fountain does not have cane protection | Outside Human Resources | 2F |  | Priority 3 | Additional Access | Provide a cane-detectable barrier skirt under the high unit. | 1 | 890
54 | Town Hall |  |  | Stair 1 | 1 |  | Priority 4 | Enhanced Usability | Recommend providing contrasting strips on stair treads. | 1 | 0
55 | Town Hall |  |  | Select Board Meeting Room | 1 |  | Priority 4 | Enhanced Usability | Recommend providing a sign at permanent rooms where no sign is provided. | 1 | 0
56 | Town Hall |  |  | Northwest Exits | 1 |  | Priority 4 | Enhanced Usability | Recommend providing handrail extensions that extend 12" past the bottom stair at exterior stairs. | 1 | 0
57 | Town Hall |  |  | Stair to Stage | 1 |  | Priority 4 | Enhanced Usability | Recommend providing a second handrail. | 1 | 0
58 | Town Hall |  |  | Stairs to Dressing Rooms | B |  | Priority 4 | Enhanced Usability | Recommend providing contrast strips on the stair treads to improve visibility of the stairs. | 1 | 0
59 | Town Hall |  |  | Egress From Dressing Room Level | B |  | Priority 4 | Enhanced Usability | Recommend providing handrails at exterior stair. | 1 | 0
60 | Town Hall |  |  | Shaded Picnic Area | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 48" wide stable, firm and slip resistant walking surface around picnic tables. | 1 | 0
61 | Town Hall |  |  | Exterior Bench | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing clear floor space alongside bench so that a wheelchair user can sit shoulder to shoulder with a person seated at the bench. | 1 | 0
62 | Town Hall |  |  | Main Entrance (East Side) | G |  | Priority 4 | Enhanced Usability | Recommend providing increased contrast at the directory sign. | 1 | 0
63 | Town Hall |  |  | Directory by Elevator | G |  |  |  | This is a good example of wayfinding signage. | 1 | 0
64 | Town Hall |  |  | Women's Toilet Room | G |  |  |  | Good example of an accessible lavatory in an accessible toilet compartments. Lavatories in the open area are compliant as well. | 1 | 0
65 | Town Hall |  |  | Corridor | G |  |  |  | Good example of a recessed fire extinguisher. | 1 | 0
1 | Underwood Pool and Bathhouse | A. Exterior Access Route | E. Obstructed by protruding objects C. Reach < 15" or > 48"(forward/side approach) | Vending Machine Building | Ext. |  | Priority 3 | Additional Access | Relocate paper towel dispenser out of the circulation path and locate so that controls are between 15"- 48" above the finished floor. | 1 | 256
2 | Underwood Pool and Bathhouse | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Sidewalk by Main Entrance to Pool | Ext. |  | Priority 1 | Program Access | Reduce cross slope to be no steeper than 1:50 (2.00%). (Cost to demolish and rebuild 10' long concrete sidewalk.) | 1 | 1250
3 | Underwood Pool and Bathhouse | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Sidewalk by Parking Lot on Cottage Street | Ext. |  | Priority 1 | Program Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost to demolish and rebuild 10' long concrete sidewalk.) | 1 | 1250
4 | Underwood Pool and Bathhouse | B. Curb Ramp | E. Transition from curb ramp to street not flush | Crosswalk Across Cottage Street From the Pool | Ext. |  | Priority 1 | Program Access | Ensure transition from curb ramp to street is flush or free of changes in level. | 1 | 170
5 | Underwood Pool and Bathhouse | B. Curb Ramp | E. Transition from curb ramp to street not flush | Sidewalk | Ext. |  | Priority 1 | Program Access | Ensure transition from curb ramp to street is flush or free of changes in level. | 1 | 170
6 | Underwood Pool and Bathhouse | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Main Entrance to Pool (Egress Doorway) | 1 |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 1116
7 | Underwood Pool and Bathhouse | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Men's and Women's Bathhouses Egress to Front | 1 |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 2 | 2232
8 | Underwood Pool and Bathhouse | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Men's and Women's Bathhouses Egress to Side (By Compartments) | 1 |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 2 | 2232
9 | Underwood Pool and Bathhouse | H. Emergency Exit | B. Tactile sign not provided at exit D. Illuminated Int. Symbol of Acc. not provided (MAAB) | Egress to Pool Deck | Ext. |  | Priority 2 | Navigational Issue | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide an illuminated sign with the International Symbol of Accessibility. | 1 | 1116
10 | Underwood Pool and Bathhouse | B. Interior Access Route | B. Obstructed by protruding objects | Men's Bathhouse Toilet Room | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier at each side of the lavatories. | 2 | 612
11 | Underwood Pool and Bathhouse | B. Interior Access Route | B. Obstructed by protruding objects | Women's Bathhouse Toilet Room | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier at each side of the lavatories. | 2 | 612
12 | Underwood Pool and Bathhouse | C. Doors, Doorways, & Gates | L. Hardware not operable with a closed fist | Pool Entrance Gate | Ext. |  | Priority 1 | Program Access | Provide ADA compliant gate hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 484
13 | Underwood Pool and Bathhouse | C. Doors, Doorways, & Gates | S. 10" solid surface not provided | Pool Entrance Gate | Ext. |  | Priority 3 | Additional Access | Swinging door and gate surfaces within 10 inches of the finished floor or ground measured vertically shall have a smooth surface on the push side extending the full width of the door or gate. | 1 | 316
14 | Underwood Pool and Bathhouse | H. Signage | G. Sign not located on the latch side of the door | Men's Bathhouse | Ext. |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
15 | Underwood Pool and Bathhouse | H. Signage | G. Sign not located on the latch side of the door | Women's Bathhouse | Ext. |  | Priority 2 | Navigational Issue | Locate sign at permanent rooms alongside the door on the latch side. | 1 | 0
16 | Underwood Pool and Bathhouse | H. Signage | Z. Sign is not compliant | Accessible Single-User Family Changing Rooms by the Main Entrance | 1 |  | Priority 2 | Navigational Issue | Due to the inadequate size of clear floor space at the transfer showers and the lack of a compliant bench, the four changing rooms by the entrance are not compliant. IHCD recommends making one single-user toilet room fully compliant and providing designation signage at the other three that does not have the International Symbol of Accessibility (ISA). (Cost for 3 signs.) | 3 | 696
17 | Underwood Pool and Bathhouse | J. Service Counter | B. Counter > 36" high | First Aid Room | 1 |  | Priority 3 | Additional Access | Provide a call button adjacent to the latch side of the door within the appropriate reach ranges indicating assistance is available by ringing the bell, with the International Symbol of Accessibility. | 1 | 400
18 | Underwood Pool and Bathhouse | J. Service Counter | B. Counter > 36" high | Lifeguard Office on Men's Bathhouse Side | 1 |  | Priority 3 | Additional Access | Provide a call button adjacent to the latch side of the door within the appropriate reach ranges indicating assistance is available by ringing the bell, with the International Symbol of Accessibility. | 1 | 400
19 | Underwood Pool and Bathhouse | J. Service Counter | B. Counter > 36" high | Lifeguard Office on Women's Bathhouse Side | 1 |  | Priority 3 | Additional Access | Provide a call button adjacent to the latch side of the door within the appropriate reach ranges indicating assistance is available by ringing the bell, with the International Symbol of Accessibility. | 1 | 400
20 | Underwood Pool and Bathhouse | O. Locker Room | R. Bench < 48" long | Accessible Single-User Family Changing Room 1 Near the Main Entrance | 1 |  | Priority 3 | Additional Access | Renovate one of the single-user shower/changing rooms by the entrance to provide a fixed bench that is 48" long for changing. Benches must be strong enough to withstand a vertical or horizontal force of 250 pounds applied at any point on the seat, fastener, mounting device, or supporting structure. A 30" wide clear floor space is required alongside the bench. | 1 | 200
21 | Underwood Pool and Bathhouse | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided E. Sign to accessible toilet not provided | Single-User Family Changing and Shower Room with Direct Access to the Pool Deck | 1 |  | Priority 1 | Program Access | Toilet room clear floor space at the toilet does not comply with 521 CMR, toilet lacks room for grab bar on the side wall and the transfer shower lacks required clear floor space. Provide a directional sign indicating the location of the nearest accessible bathing room and provide a designation sign at the toilet room that does not contain the International Symbol of Accessibility (ISA). | 2 | 464
22 | Underwood Pool and Bathhouse | B. Lavatory | E. Plumbing underneath is exposed | Men's Bathhouse Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
23 | Underwood Pool and Bathhouse | C. Single-User Toilet | O. Hook located > 48" high | Accessible Single-User Family Changing Room 1 Near the Main Entrance | 1 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150
24 | Underwood Pool and Bathhouse | D. Toilet Compartment | R. Coat hook > 48" | Men's Bathhouse Toilet Room | 1 |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
25 | Underwood Pool and Bathhouse | D. Toilet Compartment | R. Coat hook > 48" | Women's Bathhouse Toilet Room | 1 |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
26 | Underwood Pool and Bathhouse | E. Urinal | C. Flush control too high or not properly located | Men's Bathhouse Toilet Room | 1 |  | Priority 3 | Additional Access | Mount flush control at 44" max. above the finished floor at one urinal. | 1 | 500
27 | Underwood Pool and Bathhouse | F. Dispensers | A. Controls > 42" high | Accessible Single-User Family Changing Room 1 Near the Main Entrance | 1 |  | Priority 3 | Additional Access | Relocate hand dryer so the operable part is 42" max. above the finished floor. | 1 | 256
28 | Underwood Pool and Bathhouse | G. Shower Compartment | B. Clear space at transfer shower > 48" x 36" G. Grab bars mounted in wrong location N. Seat is not padded (MAAB) | Accessible Single-User Family Changing Room 1 Near the Main Entrance | 1 |  | Priority 3 | Additional Access | Renovate one of the single-user shower/changing rooms by the entrance to provide a 48" x 36" clear floor space for a transfer shower. Ensure grab bars are not provided over the seat. Provide a padded shower seat. | 1 | 6072
29 | Underwood Pool and Bathhouse | G. Shower Compartment | N. Seat is not padded (MAAB) Z. Side edge of seat > 1-1/2" from the adjacent wall | Men's Bathhouse and Women's Bathhouse Accessible Shower | 1 |  | Priority 3 | Additional Access | Provide a padded shower seat. Locate the side edge of the seat so that it is 1-1/2" max. from the adjacent wall. | 2 | 1200
30 | Underwood Pool and Bathhouse | A. Swimming Pool | C. Cross slope > 1:50 (2.00%) | Family Pool With Zero Depth Sloped Entry | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). (Cost beyond project scope.) | 1 | 0
31 | Underwood Pool and Bathhouse |  |  | Lap Swimming and Diving Pool | Ext. |  |  |  | Note: Pool entry unable to be fully surveyed. | 1 | 0
32 | Underwood Pool and Bathhouse |  |  | Accessible Single-User Family Changing Room 1 Near the Main Entrance | 1 |  |  |  | The baby changing tables are mounted at an accessible height. | 1 | 0
33 | Underwood Pool and Bathhouse |  |  | Parking Lot | Ext. |  |  |  | Parking lot has a compliant van accessible parking space. | 1 | 0